## Sprint 1
User Story | TO DO | In Progress | Impediment | To Verify | Done
1 User Type, User/Customer Login,Admin Login, Customer[Jatin Pokale] | 1.1 Develop repositories, services, controllers for UserType login | Developing methods |  |  | Developing Repository, buisness model, controllers, models
2. Bus Availability Enquirty[Swarali Shitole] | 2.1 Develop repositories,services,controllers for Bus Enquiry | maintaining changes in database |  |  | Developing Repository, buisness model, controllers, models
3. Reservation [Nidhi Jha] | 3.1 Develop repositories,services,controllers for Reservation | maintaining changes in database |  |  | Developing Repository, buisness model, controllers, models
4. Payments [SaiKrishnai] | 4.1 Develop repositories,services,controllers for Payments | maintaining changes in database |  |  | Developing Repository, buisness model, controllers, models

## Sprint 2
User Story | TO DO | In Progress | Impediment | To Verify | Done
1 User Type, User/Customer Login,Admin Login, Customer[Jatin Pokale] | 1.1 Develop the angular components for UserType login 1.2 Integrate Front end and back end | UI Design and Developing methods |  |  | Developed Components for logins, Registration, Profile, Registered components
2. Bus Availability Enquirty[Swarali Shitole] | 2.1 Develop the angular components for Bus enquiry 2.2 Integrate Front end and back end | developing UI and maintaining changes in database |  |  | Developed Components for Add Bus, Update Bus, Delete Bus Availability, Registered components
3. Reservation [Nidhi Jha] | 3.1 Develop the angular components for Reservation 3.2 Integrate Front end and back end | developing UI and maintaining changes in database |  |  | Developed Book Tickets, View Tickets, Cancel Ticket components, Registered Components
4. Payments [SaiKrishnai] | 3.1 Develop the angular components for Payments 3.2 Integrate Front end and back end | developing UI and maintaining changes in database |  |  | Developed Payments Components, Feedback, Registered components